## Sheet1
No. | Issue | Descriptions | How To Replicate | Solution | Module
SHOTCLOCK ISSUES:
1 | Display Flickering on shotclock and main displays is too obvious. | Display is on and off if observed on slowmotion using camera. | Use monile phone to observe the on and off of displays with 4543 IC instead of always on. Other displays though without 4543 IC like the colon, period, position LEDs are expected to be observed going on and off. | 4/22: Okay. Almost no flicker observed anymore.
2 | Shotclock delay is too obvious | Shotclock display in controller compared to shotclock module is a little ahead. | Compare controller display with shotclock display. Running Time delay though is acceptable so maybe time data updating and sending to shotclock module can be replicated on shotclock. | 4/22: Okay. Almost same with the controller now.
3 | Shotclock off mode in shotclock is incorrect. | When controller shotclock is manually switched off or shotclock is supposedly off when time is less than shotclock, shotclcok will still show " 0" instead of blank. | Mnaually switch of the shotclock from the controller or run the running time until it's below 24s or 14s and check the shotclock display. | 4/22: Okay. Resolved.
4 | Time format between controller and modules is not the same. | When minutes is below 10, minutes is still showing 10's digit "0" as opposed to blank like in thee controller. Same issue on seconds when the time is below 10 seconds. Copy controller time format. | Run the time and observe the issue highlighted. | 4/22: Okay. Resolved.
5 | Hold time to "0.0" when it's over until time On/Off button is pressed. | Time must be retained to "0.0" when it's over until time On/Off button is pressed. This is exactly the same improvement done on shotclock when time runs out. | Run the time until it becomes zero and don't press any buttons. Time must not reset to "10:00" right away after the buzzer. | 4/22: Okay. Resolved.
6 | Shotclock Time out LED must be switched On when shotclock OR running time becomes zero. | This port can also be used to drive a relay to switch on the light around the ring board when time is over. | Run the shotclock and/or time until becomes zero and check if Time out LED is On. Can be swtiched Off back together with the resetting of time or shotclock when a button is pressed. | 4/22: still to be checked.
7 | Clock mode in shotclock and main displays is not correct yet. | When Clock mode is enabled by pressing for more than 3s the controller Time On/Off button, the clock data shown in the controller is not replicated in the shotclock and main display time. Also, other displays must also be switched off at the start (including the controller) unless any other buttons is pressed. New Issue: "P" in Team Fouls will show up since it utilizes the blank data FF. Improvement will be HW for this. Okay for now. | Enable clock mode and check the conditions highlighted. | 4/22: Okay. Resolved.
MAIN DISPLAY ISSUES:
8 | Time delay is too obvious | Time in controller compared to main display time is a little ahead. | Compare controller time with main display time. Surprisingly, time delay in shotclock is acceptable. Maybe time data updating and sending to shotclock module can be copied. | 4/22: Okay. There's still delay but should be acceptable now.
9 | Time format between controller and modules is not the same. | When minutes is below 10, minutes is still showing 10's digit "0" as opposed to blank like in thee controller. Same issue on seconds when the time is below 10 seconds. Copy controller time format. Same issue with shotclock issue #3. | Run the time and observe the issue highlighted. | 4/22: Okay. Resolved.
10 | Hold time to "0.0" when it's over until time On/Off button is pressed. | Time must be retained to "0.0" when it's over until time On/Off button is pressed. This is exactly the same improvement done on shotclock when time runs out. | Run the time until it becomes zero and don't press any buttons. Time must not reset to "10:00" right away after the buzzer. | 4/22: Holding zero is resolved but the quick reseting is still there. Reset must only be possible after buzzer stops or after 3 seconds.
11 | Clock mode in shotclock and main displays is not correct yet. | When Clock mode is enabled by pressing for more than 3s the controller Time On/Off button, the clock data shown in the controller is not replicated in the shotclock and main display time. Also, other displays must also be switched off at the start (including in the controller) unless any other buttons is pressed. New HW Issue: "P" in Team Fouls will show up since it utilizes the blank FF data. Improvement needs to be in HW side on this. | Enable clock mode and check the conditions highlighted. | 4/22: Original issue is resolved but a new HW issue is now observed.
12 | Ghost display on LEDs with no 4543 drivers like in Period, 100's & position LEDs. | Off LEDs in Period, 100's & position are slightly lit. I think this is the result of accidental switching on of LEDs during switching the decoder to another data since the switching is done by 1 bit at a time. This can be improved if updating the decoder 4 inputs is done all at once or D input (SD2) can be used because if D input bit is switch to high first or low last, no displays connected to the decoder outputs 0~7 will be accidentally switched on. During transition only output 8 & up will be accidentally switched on which is okay because these pins are not used or connected. | Observe the LED displays mentioned & observe the faint lights on off LEDs. | 4/22: Still present. Some HW improvements will be done but on Period LEDs, ghosting is related to Time Minutes data i.e. whatever the data shown in the minutes, the corresponding LEDs in the Period is slightly lit. Check video on this for more understanding.
13 | Other LED's connections are switched or strange. Home Position LED always on. | Lower Colon LED is not on. If Guest position LED is switched on in the controller, Home position LED will light up instead. Same opposite result will hapen if Home position LED is switched on in the controller. Guest 100's LED is asiigned to D6 instead of D5. | D0 = Upper Colon LED; D1 = Lower Colon LED; D2 = Home Position LED; D3 = Guest Position LED; D4 = Home 100's LED; D5 = Guest 100's LED | 4/22: Okay. Resolved.
14 | Change Foul data display to display "P" on 8 & 9 fouls in main display only. | When Team Fouls in controller reaches 8 and 9, display blank (F data) in main display iso that the "P" (for penalty) will the only one be seen in main display. | New changes to be made. | 4/22: With the new issue observed in Issue #11, this needs to be revisitted.
15 | Change Team Remaining Timeout zero to blank in main display only. | When Team Remaining Timeouts become zero, blank (F data)should be shown instead so that no dots will be shown in main display i.e. 4dots --> 3dots --> 2dots --> 1dots --> Blank. | New changes to be made. | 4/22: Okay. Done.
16 | Option for switcheable Wifi passwords on site. | Use the extra input pin in the Wifi Mini (A0) to set two passwords for Wifi. If A0 is high, use password A. If A0 is low, use password B. Consiquently, in the controller, check switch 24/14 button if pressed during powering up. If not pressed, use password A otherwise B. This is to prepare if two scoreboards will be used at the same time in close proximity. | New changes to be made. | 4/22: Okay. Done.
17 | Add "E" to period sequence. | Instead of only 0 to 4 period, add "E" after 4 for extended period situation both in controller & main displays. | New changes to be made. | 4/22: Okay. Done.
New ISSUES:
18 | Shotclock on/off operation changed. | When 24/14 Preset Button is pressed while shot clock is on, shotclock should not stop counting down like before. Now it will stop everytime 24/14 Preset Button is pressed. | Run the shotclock and press the 24/14 Preset Button.
19